### 2026–2030 Strategic Plan

Purpose of this Document
This Strategic Plan serves as a roadmap for the Riverside Fire Authority to guide its mission, goals, and resource allocation over the next five years. It outlines the department’s priorities, identifies community needs, and sets measurable objectives to ensure the highest levels of service delivery, safety, and operational readiness.

Why Strategic Planning Matters
In an evolving landscape of community growth, fiscal constraints, and increasing service demands, strategic planning enables fire departments to remain focused, accountable, and proactive.

By clearly defining strategic priorities—such as workforce development, emergency response capability, infrastructure, and community engagement—this plan ensures that Riverside Fire Authority can make informed decisions, adapt to changing conditions, and continue to deliver appropriate, professional and effective fire and emergency services.

Commitment to Progress
The Strategic Plan is a living document that will be reviewed annually and updated as necessary to reflect new challenges, opportunities, and progress toward established goals. Through transparency and accountability, the Riverside Fire Authority remains committed to serving with integrity, excellence, and innovation.

This key can be used to decipher the deliverable timelines for the following strategic objectives:

Annual Action Plan – Check-off items throughout the course of the year to assist in maintaining the Master Planning Continuum

YEAR Action Plan – Specific objectives that have been approved and funding allocated toward with a desired goal for completion within the upcoming year.

Short Term Plan – Objectives that may be funded or are not anticipated to need funding to complete. Objectives in the Short-Term Plan have not been started. These objectives may require additional planning or design in order to begin. These projects do not need Board approval to begin, but may require Board approval of the finished product (policy updates, etc.)

Mid-Range Plan – Objectives that are not currently funded or approved, but are viewed as necessary to achieve Authority strategic goals.

Strategy #1

“Through visionary leadership and effective management practices ensure cost effective and operationally efficient services to our citizens.”

| Strategic Goal #1A |  |  |
| --- | --- | --- |
| “To provide a system for planning, organizing, leading, and evaluating the programs and services of the organization to accomplish the mission of the RFA.” (Administration and Governance) |  |  |
| Objectives |  |  |
| 1A1 | Approve upcoming year Action Plan in conjunction with budget approval | Annual Action Plan |
|  | Admin Staff | Q4 |
| 1A2 | Review and Revise Annual Action Plan | Annual Action Plan |
|  | Admin Staff | Q4 |
| 1A3 | Review and Revise Short Range Plan | Annual Action Plan |
|  | Admin Staff | Q4 |
| 1A4 | Review and Revise Mid-Range Plan | Annual Action Plan |
|  | Admin Staff | Q2-3 |
| 1A5 | Develop training and education plan for Administrative and Legislative section personnel | Mid-Range Plan |
|  | Admin Staff | 2027 |
| 1A6 | Designate resource to fund a full-time administrative assistant hours to support records retention for human resources, training and inventory | Mid-Range Plan |
|  | Admin Staff | 2027-2028 |
| 1A7 | Develop succession plans for all administrative positions, beginning with Assistant Chief of Operations & Training and District Secretary | 2026 Action Plan |
|  | Admin Staff | Q3 |
| 1A8 | Review and update all Authority Operating Policy | Short Range Plan |
|  | All staff | 2026-2027 |

| Strategic Goal #1B |  |  |
| --- | --- | --- |
| “To provide and maintain an efficient and effective operational structure to achieve the RFA’s mission and goals” (Organizational Design) |  |  |
| Objectives |  |  |
| 1B1 | Review and revise Organizational Design chart to align with service model priorities | Annual Action Plan |
|  | Admin Staff | Q4 |

| Strategic Goal #1C |  |  |
| --- | --- | --- |
| “To identify, quantify, document and project the fiscal expenditures and available financial resources needed to accomplish the mission of the RFA.” (Financial Management) |  |  |
| Objectives |  |  |
| 1C1 | Update Finance Model | Annual Action Plan |
|  | Finance Officer, Fire Chief | Q1 |
| 1C2 | Review Fiscal Policies for internal and legal accuracy | Annual Action Plan |
|  | Finance Officer, Fire Chief | Q1 |
| 1C3 | Plan grant program targets and application timelines | Annual Action Plan |
|  | Admin Staff, Program Coordinators | Q1 |
| 1C4 | Review & revise fee schedules | 2026 Action Plan |
|  | Admin Staff | Q4 |
| 1C5 | Review & revise cost recovery program | 2026 Action Plan |
|  | Admin Staff | Q2 |
| 1C6 | Implement cost recovery / property tax substitute for tax exempt properties | Mid-Range Plan |
|  | Admin Staff | 2026-2027 |
| 1C7 | Determine feasibility and implement impact fees | Mid-Range Plan |
|  | Admin Staff | 2026-2027 |
| 1C8 | Develop alternative revenue sources / enterprise services for expanded service models, including enhanced rescue capabilities, fee for service training and education services and expanded scope of Emergency Medical Services | Mid-Range Plan |
|  | Admin Staff, Program Coordinators | 2026-2028 |

| Strategic Goal #1D |  |  |
| --- | --- | --- |
| “To assure required records are created and retained and that relevant and accurate information is available to all who have a need to be informed about the activities and aspirations of the RFA.” (Information Management) |  |  |
| Objectives |  |  |
| 1D1 | Develop a short, mid and long-range electronics information and equipment replacement program. | Mid-Range Plan |
|  | Program Coordinator | 2026 |
| 1D2 | Revise policies for internet-intranet, social media, AI | Short Range Plan |
|  | Admin Staff | 2026-2027 |
| 1D3 | Conduct a cybersecurity vulnerability assessment through the Washington State Auditor’s Office #BeCyberSmart program. | Short Range Plan |
|  | Admin Staff, Program Coordinator | 2026-2027 |

| Strategic Goal #1E |  |  |
| --- | --- | --- |
| “To regularly monitor the effectiveness and efficiency of fire authority operations and service delivery with respect to its mission in the community.” (Performance and Accountability) |  |  |
| Objectives |  |  |
| 1E1 | Prepare Annual Report | Annual Action Plan |
|  | Admin Staff | Q1 |
| 1E2 | Conduct performance comparisons with similar agencies using the WA SAO FIT or equivalent | Annual Action Plan |
|  | Admin Staff | Q3 |
| 1E3 | Maintain WSRB Protection Class Rating of 5 or better | Mid-Range Plan |
|  | Admin Staff, Program Coordinators | 2027-2028 |
| 1E4 | Establish a customer survey program | Mid-Range Plan |
|  | Admin Staff | 2026-2027 |
| 1E5 | Involve greater community participation for next cycle of Mid-Range and Long-Term Plan updates | Mid-Range Plan |
|  | Admin Staff | 2028-2029 |
| 1E6 | Maintain situational awareness of opportunities to collaborate, both formally and informally, with neighboring and regional entities for service delivery | Mid-Range Plan |
|  | Admin Staff | 2026-2030 |
| 1E7 |  |  |

Strategy #2

“Prepare, coordinate, respond and, to the extent possible, mitigate emergency and non-emergency requests for service from the residents of RFA, visitors and partner agencies”

| Strategic Goal #2A |  |  |
| --- | --- | --- |
| “To reduce the risk to life, property and community vitality that may be threatened by emergency and non-emergency situations.” (Emergency Response) |  |  |
| Objectives |  |  |
| 2A1 | Review Annual Report to identify and develop solutions for service level gaps | Annual Action Plan |
|  | Fire Chief, Operations Chief | Q2-3 |
| 2A2 | In conjunction with Community Risk Analysis project, inventory target hazards and review response plans for each | Short Range Plan |
|  | Fire Chief, Operations Chief, Prevention Chief | 2026-2027 |
| 2A3 | Establish operating policy for development and maintenance of internal disaster response plans and continuity of operations | Short Range Plan |
|  | Admin Staff | 2026-2027 |

Strategy #3

“Provide and support community activities to reduce morbidity, mortality and property loss due to accident or incident including plan review, code enforcement, and fire origin and cause investigations.”

| Strategic Goal #3A |  |  |
| --- | --- | --- |
| “To identify and prioritize local risks, followed by the integrated and strategic investment of resources to reduce their occurrence and impact” (Community Risk Reduction section) |  |  |
| Objectives |  |  |
| 3A1 | Complete a formalized Community Risk Analysis | Mid-Range Plan |
|  | Admin Staff | 2026-2027 |
| 3A2 | Develop focused mechanisms aimed at mitigating the levels of risk present in our community that contribute to injury and loss, as determined by Community Risk Analysis | Mid-Range Plan |
|  | Admin Staff, Program Coordinators | 2026-2028 |
| 3A3 | Develop formalized Community Risk Reduction Plan | Mid-Range Plan |
|  | Admin Staff, Program Coordinators | 2026-2028 |
| 3A4 | Improve annual inspections of all occupancies. | Mid-Range Plan |
|  | Prevention Staff, Operations Staff | 2026-2028 |
| 3A5 | Develop and maintain at least 2 fire investigation trained personnel per shift | Mid-Range Plan |
|  | Prevention Chief, Operations Chief, Program Coordinators | 2026-2028 |

Strategy #4

“Educate and train emergency responders to be efficient and effective with an emphasis on personal and team safety through proactive risk management awareness and practices.”

| Strategic Goal #4A |  |  |
| --- | --- | --- |
| “Educate and train emergency responders to be efficient and effective with an emphasis on personal and team safety through proactive risk management awareness and practices.” |  |  |
| Objectives |  |  |
| 4A1 | Review Annual Report to identify and develop solutions for training program needs | Annual Action Plan |
|  | Operations Chief, Program Coordinators | Q2-3 |
| 4A2 | Update Professional Development program to improve leadership curriculum | Mid-Range Plan |
|  | Operations Chief, Program Coordinators | 2026-2027 |
| 4A3 | Develop and implement a formalized peer support program | 2026 Action Plan |
|  | Admin Staff, Program Coordinator | Q2 |
| 4A4 | In conjunction with Community Risk Analysis and target hazard response plan inventory projects, assure training program capabilities are adequate to meet community planning and response needs | Mid-Range Plan |
|  | Operations Chief, Program Coordinators | 2026-2028 |
| 4A5 | Formalize policy, SOG, FOG and training materials to mitigate stored energy incidents | Mid-Range Plan |
|  | Operations Chief, Program Coordinators | 2026 |
| 4A6 | Implement training program updates to improve the use of remote access options for volunteer personnel, when appropriate | Mid-Range Plan |
|  | Operations Chief, Program Coordinators | 2026-2027 |

Strategy #5

“Assemble and maintain sufficient quantities of supplies and materials in appropriate locations that ensure zero interruptions in services provided by the Operations Section with a keen attention to quality and cost.”

| Strategic Goal #5A |  |  |
| --- | --- | --- |
| “To provide and maintain efficient, effective and safe facilities to house the apparatus, equipment and personnel in strategic locations throughout the RFA as necessary to carry out our Mission” (Facilities) |  |  |
| Objectives |  |  |
| 5A1 | Review facilities reserve fund/schedule and revise where necessary | Annual Action Plan |
|  | Admin Staff | Q2-3 |
| 5A2 | Update capital facilities plan | Mid-Range Plan |
|  | Admin Staff | 2026-2027 |
| 5A3 | Develop Station 1 replacement plan, including site study and construction plan. | Mid Range Plan |
|  | Admin Staff | 2027-2029 |

Strategy #6

“Procure, deploy and maintain equipment necessary to complete mission critical activities with the highest possible degree of reliability and safety.”

| Strategic Goal #6A |  |  |
| --- | --- | --- |
| “To provide and maintain an economically efficient and operationally effective vehicle fleet and the equipment needed to safely carry out the mission of the RFA” (Vehicles & Equipment) |  |  |
| Objectives |  |  |
| 6A1 | Review equipment and apparatus reserve funds/schedules and revise where necessary | Annual Action Plan |
|  | Admin Staff | Q2-3 |
| 6A2 | Update fleet and equipment needs for update of capital facilities plan | Short Range Plan |
|  | Admin Staff | 2026-2027 |
| 6A3 | Develop contingency plan for alternative source(s) to provide apparatus maintenance and repair | Mid-Range Plan |
|  | Admin Staff | 2027-2029 |
| 6A4 | Finalize replacement plan and schedule for Ladder 2 | Mid-Range Plan |
|  | Admin Staff | 2026 |